## General
Project Details
Item | Value
Project: | [Sample project name]
PRCI Project Code: | [XXX-00-00A]
Contractor Project Code: | [RRU-21-0025]
Contract Number: | [TBD]
Contractor: | [Research R Us]
Principal Investigator: | [I. L. Findout]
PI Email: | [ilfindoubt@rrus.com]
Contracting Contact: | [U. Signhere]
CC Email: | [usignhere@rrus.com]
Invoicing Contact: | [U. O. Me]
IC Email: | [uome@rrus.com]
Start Date | 2023-10-01
General notes, directions
Item | Note
1 | All milestones should be in the same fiscal year. I.e., all milestones for the first funding year are 1; use 2 for the second year, etc.
2 | PRCI research fiscal years begin January 1 of each year
3 | To add more rows to a table, click any cell inside the table. Then right click and select insert row (above or below as desired).
4 | Delete unused rows from tables
5 | Master milestone/tasks should be on the budget tab, the schedule will look up the associated data
6 | The user can also add non milestone-task items to the schedule such as milestone checks or project team tasks. Simply type 'N/A' for the task number and a corresponding description on the Schedule tab.
7 | Replace anything within (and including the) square brackets ('[]') with project specific information. For unknown information (e.g., contract number at the proposal time), use 'TBD'.

## Budget
Project: [XXX-00-00A], [Sample project name]
Contractor: [Research R Us]
Updated by: [Individual completing the form]
As of: [MM/DD/YYYY]
250000
Milestone | Task | MS_Task | Task Name | Task Deliverable | Deliverable Quanity | Unit Cost | Extended Cost | Row Labels | Cost by Year
1 | 1 | 1_1 | Project kickoff | Kickoff meeting | 1 | 2500 | 2500 | 1 | 119510
1 | 2 | 1_2 | Literature review | Literature review document | 1 | 15800 | 15800 | 2 | 130490
1 | 3 | 1_3 | Develop test plans | Written test plan | 2 | 19250 | 38500 | Grand Total | 250000
1 | 4 | 1_4 | Test setup | Piping and control confuration | 2 | 31355 | 62710
2 | 1 | 2_1 | Flow testing | Flow testing and data gathering | 2 | 25825 | 51650
2 | 2 | 2_2 | Data analysis and regression | Data reduction and analysis in Excel | 2 | 15850 | 31700
2 | 3 | 2_3 | Draft report | Draft final report | 1 | 22140 | 22140
2 | 4 | 2_4 | Revise draft | Final deliverable (Article 2B) | 1 | 25000 | 25000
To add more data, Insert new rows ABOVE this one, otherwise, delete unused rows

## Schedule
Project: [XXX-00-00A], [Sample project name] | [13 empty] | Legend:
Contractor: [Research R Us] | [13 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Behind |  |  |  |  | Completed |  |  |  |  | Unassigned
Updated by: [Individual completing the form] | [13 empty] | 2023-10-01
As of: [MM/DD/YYYY] | [9 empty] | 250000 | 0 | 0 | 0 |  | October |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July
MS_Task | Task Name | Notes/Comments | Category | Progress | Start | No. Weeks | No. Days | Offset Weeks | End Date | Task $ | Burn $ | Invoiced $ | To Invoice $ | time axis 2023-10-01 to 2025-06-29
1_1 | Project kickoff |  | Completed | 0 | 2023-10-01 | 1 | 7 |  | 2023-10-08 | 2500 | 0 | 0 | 0
1_2 | Literature review |  | Completed | 0 | 2023-10-08 | 4 | 28 | 0 | 2023-11-05 | 15800 | 0 | 0 | 0
1_3 | Develop test plans |  | Completed | 0 | 2023-11-12 | 6 | 42 | 1 | 2023-12-24 | 38500 | 0 | 0 | 0
1_4 | Test setup | Project team task | Completed | 0 | 2023-12-24 | 4 | 28 | 0 | 2024-01-21 | 62710 | 0 | 0 | 0
2_1 | Flow testing |  | Med Risk | 0 | 2023-12-10 | 7 | 49 | -6 | 2024-01-28 | 51650 | 0 | 0 | 0
2_2 | Data analysis and regression |  | High Risk | 0 | 2024-02-11 | 5 | 35 | 2 | 2024-03-17 | 31700 | 0 | 0 | 0
2_3 | Draft report |  | Med Risk | 0 | 2024-03-03 | 8 | 56 | -2 | 2024-04-28 | 22140 | 0 | 0 | 0
2_4 | Revise draft |  | Low Risk | 0 | 2024-04-14 | 12 | 84 | -2 | 2024-07-07 | 25000 | 0 | 0 | 0
To add more data, Insert new rows ABOVE this one, otherwise, delete unused rows
Note on G5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of weeks required to complete the task
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of weeks after (before) the start of the previous task when this task begins
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The amount, by task, in $, that has been completed and could be or has been invoiced.
Note on M5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The amount that has been submitted as an invoice.
Note on N5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The amount that is yet to be invoiced.